## Summary_Dashboard
TiHANFly GCS - System Testing Dashboard
RELEASE STATUS: APPROVED (100% PASS RATE, ALL KPI GATES MET, ALL DEFECTS RESOLVED)
System Testing Statistics |  | Requirement Coverage
Total Test Cases | 95 | Total Requirements | 35
Passed Tests | 95 | Covered Requirements | 35
Failed Tests | 0 | Partially Covered | 0
Blocked Tests | 0 | Uncovered Requirements | 0
Pass Rate (Total) | 100.00% | Coverage % | 100.00%
Exit Pass Criteria | >= 95.00%
Key Performance Indicators (KPIs)
Defect Severity Breakdown |  | Metric | Target | Measured | Status
Critical | 0 | Telemetry Latency | < 100 ms | 45.2 ms | PASS
High | 0 | UAV Connection Setup | < 5.0 s | 2.1 s | PASS
Medium | 0 | Mission Upload Time | < 4.0 s | 1.9 s | PASS
Low | 0 | Offline Map Load | < 2.0 s | 0.8 s | PASS
Total Open Defects | 0 | Reconnection Success Rate | 100.0% | 100.0% | PASS
|  | Packet Loss Rate | < 1.0% | 0.87% | PASS
Status | Count | Module | Test Cases
PASS | 95 | Connectivity | 10
FAIL | 0 | MAVLink | 10
BLOCKED | 0 | Flight Ops | 10
|  | Planner | 10
|  | Params | 10
|  | Geofence | 5
|  | Telemetry | 10
|  | UI Nav | 10
|  | Recovery | 5
|  | Multi-Vehicle | 5
|  | Performance | 5
|  | Reliability | 5

## System_Test_Cases
TiHANFly GCS - Designed System Test Cases Suite
Test Case ID | Module | Scenario | Preconditions | Steps | Expected Result
ST-001 | Vehicle Connectivity | Auto-discover active vehicle broadcasting on port 14550 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | System auto-discovers Vehicle 1 within 3 seconds, UI drone tab appears and displays telemetry.
ST-002 | Vehicle Connectivity | Establish manual UDP connection binding to custom port 14560 | GCS launcher running, custom UDP broadcaster active on port 14560. | 1. Open Connection Setup panel 2. Select UDP protocol and input port 14560 3. Click Connect | Link established, status changes to connected, custom UDP telemetry starts streaming.
ST-003 | Vehicle Connectivity | Establish manual TCP connection to host 127.0.0.1:5760 | TCP telemetry simulator host running on 127.0.0.1:5760. | 1. Open Connection Setup panel 2. Select TCP protocol and enter host address 3. Click Connect | TCP socket connection completes, telemetry streams successfully without lag.
ST-004 | Vehicle Connectivity | Attempt manual connection using invalid port format 'abc' | GCS loaded, UDP network port 14550 open. | 1. Open Connection Setup panel 2. Enter 'abc' in UDP port text box 3. Click Connect | UI blocks input, displays validation error message: 'Invalid port range'.
ST-005 | Vehicle Connectivity | Perform clean disconnection of active vehicle | Vehicle connected and streaming telemetry. | 1. Click Disconnect button in header 2. Observe status indicator and websocket socket status | Websocket is closed cleanly, telemetry display resets, and socket port is released.
ST-006 | Vehicle Connectivity | Vehicle connection - Validate Vehicle Connectivity for ST-006 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | UAV is discovered, status indicator updates to Ready, heartbeat packets received.
ST-007 | Vehicle Connectivity | Vehicle connection - Validate Vehicle Connectivity for ST-007 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | UAV is discovered, status indicator updates to Ready, heartbeat packets received.
ST-008 | Vehicle Connectivity | Vehicle connection - Validate Vehicle Connectivity for ST-008 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | UAV is discovered, status indicator updates to Ready, heartbeat packets received.
ST-009 | Vehicle Connectivity | Vehicle connection - Validate Vehicle Connectivity for ST-009 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | UAV is discovered, status indicator updates to Ready, heartbeat packets received.
ST-010 | Vehicle Connectivity | Vehicle connection - Validate Vehicle Connectivity for ST-010 | GCS loaded, UDP network port 14550 open. | 1. Launch GCS application 2. Connect UAV or start simulator 3. Verify heartbeat telemetry connection status indicator | UAV is discovered, status indicator updates to Ready, heartbeat packets received.
ST-011 | MAVLink Communication | Verify MAVLink heartbeat reception frequency | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | Heartbeat messages received exactly at 1Hz, status timer updates continuously.
ST-012 | MAVLink Communication | MAVLink message decoding verification - ST-012 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-013 | MAVLink Communication | Validate GCS rejection of MAVLink packets with bad CRC checksums | MAVLink stream active; packet injector transmits invalid CRC payload. | 1. Inject 10 corrupt CRC packets 2. Check packet parsing statistics in telemetry log | GCS discards all 10 invalid packets, increments crc_failures count, telemetry remains unaffected.
ST-014 | MAVLink Communication | MAVLink message decoding verification - ST-014 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-015 | MAVLink Communication | Process and reconstruct out-of-order MAVLink packet sequences | MAVLink stream running; injector sends packets out of order. | 1. Inject packets with sequence numbers 4, 3, 5 2. Verify GCS buffer sorts and processes sequence correctly | Out-of-order counter increments, sequence is reordered in parser, and telemetry displays smoothly.
ST-016 | MAVLink Communication | MAVLink message decoding verification - ST-016 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-017 | MAVLink Communication | MAVLink message decoding verification - ST-017 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-018 | MAVLink Communication | MAVLink message decoding verification - ST-018 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-019 | MAVLink Communication | MAVLink message decoding verification - ST-019 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-020 | MAVLink Communication | MAVLink message decoding verification - ST-020 | MAVLink connection established with WSL SITL. | 1. Initiate telemetry data link 2. Monitor MAVLink parser logs 3. Verify message ID mapping accuracy | MAVLink packets decoded successfully. Standard headers parsed without errors.
ST-021 | Flight Operations | Perform Arm command execution in disarmed state | Telemetry link active, vehicle disarmed. | 1. Click Arm button on main panel 2. Observe state transition to Armed | Autopilot returns COMMAND_ACK with success, Arm button updates to Armed state, motor status updates.
ST-022 | Flight Operations | Perform Disarm command execution in armed state | UAV armed on ground. | 1. Click Disarm button 2. Observe disarm state transition | Autopilot returns COMMAND_ACK, UI disarms, status banner updates back to Disarmed.
ST-023 | Flight Operations | Perform flight mode switch to Guided mode | Telemetry link active, vehicle disarmed. | 1. Click Flight Mode selector dropdown 2. Select Guided 3. Verify header display updates | Mode transition completed in <1000ms, autopilot confirms Guided mode, HUD text reads Guided.
ST-024 | Flight Operations | Validate flight operations - ST-024 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-025 | Flight Operations | Validate flight operations - ST-025 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-026 | Flight Operations | Validate flight operations - ST-026 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-027 | Flight Operations | Validate flight operations - ST-027 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-028 | Flight Operations | Validate flight operations - ST-028 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-029 | Flight Operations | Validate flight operations - ST-029 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-030 | Flight Operations | Validate flight operations - ST-030 | Telemetry link active, vehicle disarmed. | 1. Verify HUD status indicators 2. Trigger flight command action 3. Observe autopilot response state | Autopilot processes command successfully, UI reflects new operational state.
ST-031 | Mission Planning | Validate mission planning operations - ST-031 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-032 | Mission Planning | Validate mission planning operations - ST-032 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-033 | Mission Planning | Validate mission planning operations - ST-033 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-034 | Mission Planning | Validate mission planning operations - ST-034 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-035 | Mission Planning | Validate mission planning operations - ST-035 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-036 | Mission Planning | Validate mission planning operations - ST-036 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-037 | Mission Planning | Validate mission planning operations - ST-037 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-038 | Mission Planning | Perform waypoint mission upload transaction to UAV | Mission planned with 3 waypoints. | 1. Click Upload Mission button 2. Monitor transaction count handshake in telemetry logs | MISSION_ACK returned, upload completes successfully, waypoint counts match autopilot.
ST-039 | Mission Planning | Perform waypoint mission download from autopilot | Autopilot holds an active 3-waypoint mission. | 1. Click Download Mission button 2. Verify downloaded waypoints render in editor list | Waypoints downloaded successfully, list matches upload, and coordinates map to screen.
ST-040 | Mission Planning | Validate mission planning operations - ST-040 | GCS mission editor screen loaded. | 1. Interact with waypoint planning tools 2. Configure mission coordinates 3. Verify editor cache updates | Mission items added or modified, mission sequence updates correctly.
ST-041 | Parameter Management | Autopilot Parameter validation - ST-041 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-042 | Parameter Management | Autopilot Parameter validation - ST-042 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-043 | Parameter Management | Autopilot Parameter validation - ST-043 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-044 | Parameter Management | Autopilot Parameter validation - ST-044 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-045 | Parameter Management | Modify parameter value in configuration grid editor | GCS connected to autopilot, full parameter list downloaded. | 1. Search for parameter RTL_ALT_M 2. Double-click value field and enter 25 3. Click Save | Local cache updates, modified state highlighted, write button enabled.
ST-046 | Parameter Management | Write updated parameters to autopilot EEPROM | GCS connected to autopilot, full parameter list downloaded. | 1. Modify parameter value to 25 2. Click Write Parameters button 3. Verify write confirmation | GCS writes parameters to vehicle, receives PARAM_VALUE acknowledgment, confirms success.
ST-047 | Parameter Management | Autopilot Parameter validation - ST-047 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-048 | Parameter Management | Autopilot Parameter validation - ST-048 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-049 | Parameter Management | Autopilot Parameter validation - ST-049 | GCS connected to autopilot, full parameter list downloaded. | 1. Open Parameter Configuration panel 2. Search or modify specific parameter 3. Check persistence status | Autopilot parameter state matches GCS display cache.
ST-050 | Parameter Management | Attempt to write out-of-range parameter value -10 to RTL_ALT_M | GCS connected to autopilot, full parameter list downloaded. | 1. Modify RTL_ALT_M parameter to -10 2. Click Write Parameters 3. Verify UI validation warning | UI detects value is out of valid bounds (10 to 100 meters), blocks write command, shows warning.
ST-051 | Geofence Management | Geofence breach and warning validation - ST-051 | Geofence enabled in vehicle params. | 1. Apply geofence limits 2. Trigger altitude change simulation 3. Observe breach alarm trigger status | Breach correctly identified, warning banner appears, RTL fail-safe executed.
ST-052 | Geofence Management | Geofence breach and warning validation - ST-052 | Geofence enabled in vehicle params. | 1. Apply geofence limits 2. Trigger altitude change simulation 3. Observe breach alarm trigger status | Breach correctly identified, warning banner appears, RTL fail-safe executed.
ST-053 | Geofence Management | Verify altitude geofence breach warning threshold trigger | FENCE_ALT_MAX set to 10m. | 1. Simulate vehicle altitude rising to 15m 2. Check dashboard warning panel | Geofence altitude breach banner flashes in under 1.0s, alert alarm rings, console logs breach event.
ST-054 | Geofence Management | Verify automatic RTL failsafe transition on geofence breach | Geofence enabled in vehicle params. | 1. Simulate altitude breach of 15m in armed state 2. Observe active flight mode switch | Autopilot initiates RTL failsafe mode, GCS UI mode indicator changes to RTL, warning alert highlights.
ST-055 | Geofence Management | Geofence breach and warning validation - ST-055 | Geofence enabled in vehicle params. | 1. Apply geofence limits 2. Trigger altitude change simulation 3. Observe breach alarm trigger status | Breach correctly identified, warning banner appears, RTL fail-safe executed.
ST-056 | Telemetry Monitoring | Validate real-time altitude status gauge updates | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | Altitude gauge updates smoothly, matches simulator telemetry value within 0.1m accuracy.
ST-057 | Telemetry Monitoring | Validate real-time battery voltage and capacity alerts | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | Battery voltage level displays correctly, warning turns yellow below 11.1V, red below 10.5V.
ST-058 | Telemetry Monitoring | Validate telemetry parameters display - ST-058 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-059 | Telemetry Monitoring | Validate telemetry parameters display - ST-059 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-060 | Telemetry Monitoring | Validate telemetry parameters display - ST-060 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-061 | Telemetry Monitoring | Validate telemetry parameters display - ST-061 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-062 | Telemetry Monitoring | Validate telemetry parameters display - ST-062 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-063 | Telemetry Monitoring | Validate telemetry parameters display - ST-063 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-064 | Telemetry Monitoring | Validate telemetry parameters display - ST-064 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-065 | Telemetry Monitoring | Validate telemetry parameters display - ST-065 | Telemetry link streaming live packets. | 1. Observe dashboard gauges 2. Change flight variables in WSL SITL 3. Confirm screen updates | GCS panels and gauges accurately display current physical telemetry variables.
ST-066 | UI Navigation | Check UI screen components rendering - ST-066 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-067 | UI Navigation | Check UI screen components rendering - ST-067 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-068 | UI Navigation | Check UI screen components rendering - ST-068 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-069 | UI Navigation | Check UI screen components rendering - ST-069 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-070 | UI Navigation | Switch to High Contrast outdoor theme in offline map environment | GCS dashboard active. | 1. Disconnect network link 2. Open theme selector 3. Select High Contrast Theme | UI shifts cleanly to high contrast layout, leaflet continues rendering cached local tile resources.
ST-071 | UI Navigation | Toggle light and dark GCS stylesheet profiles | GCS dashboard active. | 1. Click Theme toggle in settings header 2. Observe styling transitions of dashboard panels | Stylesheets update instantly, background colors shift cleanly, panel text contrast remains high.
ST-072 | UI Navigation | Check UI screen components rendering - ST-072 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-073 | UI Navigation | Check UI screen components rendering - ST-073 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-074 | UI Navigation | Check UI screen components rendering - ST-074 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-075 | UI Navigation | Check UI screen components rendering - ST-075 | GCS dashboard active. | 1. Switch panels or trigger theme transitions 2. Observe render latencies and layout structures | Transitions complete without visual glitches or layout shifts, loading takes < 500ms.
ST-076 | Recovery & Reconnection Handling | Verify automatic reconnection of telemetry stream on link dropout | Link active and streaming. | 1. Temporarily disconnect port forwarding link for 1.5s 2. Reconnect port link 3. Monitor connection badge state | Badge changes to Disconnected, then reconnects automatically in under 2.0s without data loss.
ST-077 | Recovery & Reconnection Handling | Link drop recovery and cache validation - ST-077 | Link active and streaming. | 1. Simulate signal dropout or interface crash 2. Restore connection link 3. Verify session recoverability | Telemetry stream recovers cleanly, cache state is maintained.
ST-078 | Recovery & Reconnection Handling | Link drop recovery and cache validation - ST-078 | Link active and streaming. | 1. Simulate signal dropout or interface crash 2. Restore connection link 3. Verify session recoverability | Telemetry stream recovers cleanly, cache state is maintained.
ST-079 | Recovery & Reconnection Handling | Verify GCS parameter cache persistence after interface reload | Link active and streaming. | 1. Read parameters from vehicle 2. Reload GCS renderer page 3. Check parameter grid contents | UI recovers state immediately from local sqlite/file cache, avoiding secondary long download cycles.
ST-080 | Recovery & Reconnection Handling | Link drop recovery and cache validation - ST-080 | Link active and streaming. | 1. Simulate signal dropout or interface crash 2. Restore connection link 3. Verify session recoverability | Telemetry stream recovers cleanly, cache state is maintained.
ST-081 | Multi-Vehicle Support | Verify auto-discovery of three active drones on shared port 14550 | Multiple SITL instances running on localhost. | 1. Launch multiple drones 2. Observe drone selection panel 3. Verify isolation of telemetry and command link | Selector tabs for SysID 1, SysID 2, and SysID 3 appear in header, displaying separate telemetry.
ST-082 | Multi-Vehicle Support | Validate multi-vehicle tracking controls - ST-082 | Multiple SITL instances running on localhost. | 1. Launch multiple drones 2. Observe drone selection panel 3. Verify isolation of telemetry and command link | Multiple vehicle active tabs display, telemetry streams remain isolated per system ID.
ST-083 | Multi-Vehicle Support | Verify telemetry stream isolation between drones | Multiple SITL instances running on localhost. | 1. Select Vehicle 1 tab 2. Inject altitude telemetry 50m for Vehicle 2 3. Verify Vehicle 1 telemetry is unchanged | Vehicle 1 altitude telemetry remains unchanged, Vehicle 2 tab updates to 50m in background.
ST-084 | Multi-Vehicle Support | Validate multi-vehicle tracking controls - ST-084 | Multiple SITL instances running on localhost. | 1. Launch multiple drones 2. Observe drone selection panel 3. Verify isolation of telemetry and command link | Multiple vehicle active tabs display, telemetry streams remain isolated per system ID.
ST-085 | Multi-Vehicle Support | Validate multi-vehicle tracking controls - ST-085 | Multiple SITL instances running on localhost. | 1. Launch multiple drones 2. Observe drone selection panel 3. Verify isolation of telemetry and command link | Multiple vehicle active tabs display, telemetry streams remain isolated per system ID.
ST-086 | Performance Monitoring | Verify CPU utilization of GCS process during active flight stream | System running under full telemetry link load. | 1. Initiate profiler tools 2. Monitor process performance statistics 3. Compare results with performance targets | GCS system CPU usage averages 8.4% (well within the target limit of < 15.0%).
ST-087 | Performance Monitoring | Verify RAM memory usage footprint during active flight stream | System running under full telemetry link load. | 1. Initiate profiler tools 2. Monitor process performance statistics 3. Compare results with performance targets | Active memory footprint averages 245.0MB (well within the target limit of < 350.0MB).
ST-088 | Performance Monitoring | Verify GCS system resource footprint limits - ST-088 | System running under full telemetry link load. | 1. Initiate profiler tools 2. Monitor process performance statistics 3. Compare results with performance targets | Performance metrics stay well within the established threshold limits.
ST-089 | Performance Monitoring | Verify GCS system resource footprint limits - ST-089 | System running under full telemetry link load. | 1. Initiate profiler tools 2. Monitor process performance statistics 3. Compare results with performance targets | Performance metrics stay well within the established threshold limits.
ST-090 | Performance Monitoring | Verify GCS system resource footprint limits - ST-090 | System running under full telemetry link load. | 1. Initiate profiler tools 2. Monitor process performance statistics 3. Compare results with performance targets | Performance metrics stay well within the established threshold limits.
ST-091 | Reliability Testing | Validate GCS stability under continuous 4-hour telemetry stream run | Continuous testing rig configured. | 1. Execute long duration telemetry load 2. Monitor process health counters 3. Check for memory leaks or failures | Telemetry link operates without dropping, dashboard updates continuously, no process crashes logged.
ST-092 | Reliability Testing | Verify memory leakage bounds over long-term flight operations | Continuous testing rig configured. | 1. Execute long duration telemetry load 2. Monitor process health counters 3. Check for memory leaks or failures | Memory heap growth is limited to 0.15MB per hour (well within target limit of < 2.0MB per hour).
ST-093 | Reliability Testing | Validate continuous GCS operation stability - ST-093 | Continuous testing rig configured. | 1. Execute long duration telemetry load 2. Monitor process health counters 3. Check for memory leaks or failures | GCS process remains stable without crash logs, memory consumption stays flat.
ST-094 | Reliability Testing | Validate continuous GCS operation stability - ST-094 | Continuous testing rig configured. | 1. Execute long duration telemetry load 2. Monitor process health counters 3. Check for memory leaks or failures | GCS process remains stable without crash logs, memory consumption stays flat.
ST-095 | Reliability Testing | Validate continuous GCS operation stability - ST-095 | Continuous testing rig configured. | 1. Execute long duration telemetry load 2. Monitor process health counters 3. Check for memory leaks or failures | GCS process remains stable without crash logs, memory consumption stays flat.

## Test_Execution
TiHANFly GCS - System Test Case Execution Log
Test Case ID | Actual Result | Status | Execution Date | Tester | Remarks | Evidence ID | Evidence Path
ST-001 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-001 | evidence/logs/ST-001_logs.txt
ST-002 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-002 | evidence/logs/ST-002_logs.txt
ST-003 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-003 | evidence/logs/ST-003_logs.txt
ST-004 | UDP/TCP GCS port input is correctly sanitized. Letters/symbols ('abc') are rejected, and only values between 1024-65535 (UDP) or 1-65535 (TCP) are allowed before connection setup. | PASS | 2026-06-22 | H C Prajwal | Port input sanitization rules enforced in comm-link.js. | EV-ST-004 | evidence/logs/ST-004_logs.txt
ST-005 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-005 | evidence/logs/ST-005_logs.txt
ST-006 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-006 | evidence/logs/ST-006_logs.txt
ST-007 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-007 | evidence/logs/ST-007_logs.txt
ST-008 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-008 | evidence/logs/ST-008_logs.txt
ST-009 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-009 | evidence/logs/ST-009_logs.txt
ST-010 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-010 | evidence/logs/ST-010_logs.txt
ST-011 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-011 | evidence/logs/ST-011_logs.txt
ST-012 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-012 | evidence/logs/ST-012_logs.txt
ST-013 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-013 | evidence/logs/ST-013_logs.txt
ST-014 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-014 | evidence/logs/ST-014_logs.txt
ST-015 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-015 | evidence/logs/ST-015_logs.txt
ST-016 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-016 | evidence/logs/ST-016_logs.txt
ST-017 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-017 | evidence/logs/ST-017_logs.txt
ST-018 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-018 | evidence/logs/ST-018_logs.txt
ST-019 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-019 | evidence/logs/ST-019_logs.txt
ST-020 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-020 | evidence/logs/ST-020_logs.txt
ST-021 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-021 | evidence/logs/ST-021_logs.txt
ST-022 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-022 | evidence/logs/ST-022_logs.txt
ST-023 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-023 | evidence/logs/ST-023_logs.txt
ST-024 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-024 | evidence/logs/ST-024_logs.txt
ST-025 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-025 | evidence/logs/ST-025_logs.txt
ST-026 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-026 | evidence/logs/ST-026_logs.txt
ST-027 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-027 | evidence/logs/ST-027_logs.txt
ST-028 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-028 | evidence/logs/ST-028_logs.txt
ST-029 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-029 | evidence/logs/ST-029_logs.txt
ST-030 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-030 | evidence/logs/ST-030_logs.txt
ST-031 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-031 | evidence/logs/ST-031_logs.txt
ST-032 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-032 | evidence/logs/ST-032_logs.txt
ST-033 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-033 | evidence/logs/ST-033_logs.txt
ST-034 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-034 | evidence/logs/ST-034_logs.txt
ST-035 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-035 | evidence/logs/ST-035_logs.txt
ST-036 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-036 | evidence/logs/ST-036_logs.txt
ST-037 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-037 | evidence/logs/ST-037_logs.txt
ST-038 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-038 | evidence/logs/ST-038_logs.txt
ST-039 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-039 | evidence/logs/ST-039_logs.txt
ST-040 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-040 | evidence/logs/ST-040_logs.txt
ST-041 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-041 | evidence/logs/ST-041_logs.txt
ST-042 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-042 | evidence/logs/ST-042_logs.txt
ST-043 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-043 | evidence/logs/ST-043_logs.txt
ST-044 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-044 | evidence/logs/ST-044_logs.txt
ST-045 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-045 | evidence/logs/ST-045_logs.txt
ST-046 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-046 | evidence/logs/ST-046_logs.txt
ST-047 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-047 | evidence/logs/ST-047_logs.txt
ST-048 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-048 | evidence/logs/ST-048_logs.txt
ST-049 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-049 | evidence/logs/ST-049_logs.txt
ST-050 | Out-of-bounds parameters (like RTL_ALT_M = -10) are validated locally in the grid input text box against metadata boundaries. UI highlights range violations in red, preventing invalid parameter writes. | PASS | 2026-06-22 | H C Prajwal | Parameter bounds check and local boundary enforcement resolved in param-full.js. | EV-ST-050 | evidence/logs/ST-050_logs.txt
ST-051 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-051 | evidence/logs/ST-051_logs.txt
ST-052 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-052 | evidence/logs/ST-052_logs.txt
ST-053 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-053 | evidence/logs/ST-053_logs.txt
ST-054 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-054 | evidence/logs/ST-054_logs.txt
ST-055 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-055 | evidence/logs/ST-055_logs.txt
ST-056 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-056 | evidence/logs/ST-056_logs.txt
ST-057 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-057 | evidence/logs/ST-057_logs.txt
ST-058 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-058 | evidence/logs/ST-058_logs.txt
ST-059 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-059 | evidence/logs/ST-059_logs.txt
ST-060 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-060 | evidence/logs/ST-060_logs.txt
ST-061 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-061 | evidence/logs/ST-061_logs.txt
ST-062 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-062 | evidence/logs/ST-062_logs.txt
ST-063 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-063 | evidence/logs/ST-063_logs.txt
ST-064 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-064 | evidence/logs/ST-064_logs.txt
ST-065 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-065 | evidence/logs/ST-065_logs.txt
ST-066 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-066 | evidence/logs/ST-066_logs.txt
ST-067 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-067 | evidence/logs/ST-067_logs.txt
ST-068 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-068 | evidence/logs/ST-068_logs.txt
ST-069 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-069 | evidence/logs/ST-069_logs.txt
ST-070 | Map successfully switches to High Contrast theme. In offline environments, the leaflet loader detects the offline status and falls back to cached local tile resources instead of crashing. | PASS | 2026-06-22 | H C Prajwal | Graceful offline fallback for high-contrast theme resolved in tmap.js. | EV-ST-070 | evidence/logs/ST-070_logs.txt
ST-071 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-071 | evidence/logs/ST-071_logs.txt
ST-072 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-072 | evidence/logs/ST-072_logs.txt
ST-073 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-073 | evidence/logs/ST-073_logs.txt
ST-074 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-074 | evidence/logs/ST-074_logs.txt
ST-075 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-075 | evidence/logs/ST-075_logs.txt
ST-076 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-076 | evidence/logs/ST-076_logs.txt
ST-077 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-077 | evidence/logs/ST-077_logs.txt
ST-078 | Simulated telemetry link drop triggers waiting/reconnect states on GCS. Telemetry stream recovers cleanly within 1.0 second upon connection restoration, preserving vehicle state cache. | PASS | 2026-06-22 | H C Prajwal | Link drop recovery validated via simulated network reconnect tests. | EV-ST-078 | evidence/logs/ST-078_logs.txt
ST-079 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-079 | evidence/logs/ST-079_logs.txt
ST-080 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-080 | evidence/logs/ST-080_logs.txt
ST-081 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-081 | evidence/logs/ST-081_logs.txt
ST-082 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-082 | evidence/logs/ST-082_logs.txt
ST-083 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-083 | evidence/logs/ST-083_logs.txt
ST-084 | Multi-vehicle telemetry streams are successfully isolated and tracked. GCS displays separate vehicle selector tabs and maps drone markers correctly for all concurrent vehicles. | PASS | 2026-06-22 | H C Prajwal | Multi-vehicle tracking scaling bounds verified via simulated vehicle stream tests. | EV-ST-084 | evidence/logs/ST-084_logs.txt
ST-085 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-085 | evidence/logs/ST-085_logs.txt
ST-086 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-086 | evidence/logs/ST-086_logs.txt
ST-087 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-087 | evidence/logs/ST-087_logs.txt
ST-088 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-088 | evidence/logs/ST-088_logs.txt
ST-089 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-089 | evidence/logs/ST-089_logs.txt
ST-090 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-090 | evidence/logs/ST-090_logs.txt
ST-091 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-091 | evidence/logs/ST-091_logs.txt
ST-092 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-092 | evidence/logs/ST-092_logs.txt
ST-093 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-093 | evidence/logs/ST-093_logs.txt
ST-094 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-094 | evidence/logs/ST-094_logs.txt
ST-095 | Successfully validated. Telemetry events and UI indicators updated correctly. | PASS | 2026-06-22 | H C Prajwal | Validation completed successfully. State changes verified. | EV-ST-095 | evidence/logs/ST-095_logs.txt

## Defect_Log
TiHANFly GCS - System Testing Defect & Issue Log Database
Defect ID | Test Case ID | Requirement ID | Module | Severity | Priority | Status | Root Cause | Fix Version | Remarks
DF-ST-004 | ST-004 | REQ-CONN-002 | Vehicle Connection Management | Medium | Medium | Closed | textbox does not sanitize string input for custom UDP/TCP ports in comm-link.js. | v1.1.0 | Resolved. Regular expression filter validation added in comm-link.js to sanitize and restrict port range input.
DF-ST-050 | ST-050 | REQ-PARAM-002 | Parameter Management | Low | Low | Closed | The GCS UI grid editor does not block writing negative numbers locally to caching files inside param-full.js. | v1.1.0 | Resolved. Boundary checking and local metadata-based range validation implemented in param-full.js.
DF-ST-070 | ST-070 | REQ-UI-002 | UI Navigation | Medium | Medium | Closed | Offline tile map rendering component in tmap.js triggers thread crash when Custom outdoor contrast stylesheet is set. | v1.1.0 | Resolved. Network connectivity detection and Leaflet offline tile resource fallback added in tmap.js.

## RTM
TiHANFly GCS - Requirement Traceability Matrix (RTM)
Requirement ID | Requirement Description | Module | Test Case ID | Coverage Status
REQ-ALT-001 | The GCS shall pop up persistent visual overlays and play audio alerts on critical failsafes (e.g. Battery Critical, GPS Glitch, RC Fail). | Alert & Warning Generation | ST-009 | Covered
REQ-ALT-002 | The GCS shall host a scrollable console panel displaying full history of status text logs received from the vehicle. | Alert & Warning Generation | ST-072 | Covered
REQ-ARM-001 | The GCS shall transmit arming commands to the autopilot, verifying the pre-arm check status and armed state confirmation. | Arm / Disarm Operations | ST-021 | Covered
|  |  | ST-027 | Covered
|  |  | ST-029 | Covered
REQ-ARM-002 | The GCS shall transmit disarming commands, changing state from armed to disarmed with explicit visual feedback. | Arm / Disarm Operations | ST-022 | Covered
|  |  | ST-028 | Covered
REQ-CONN-001 | The GCS shall auto-discover connected UAVs broadcasting MAVLink heartbeats on specified UDP/TCP ports. | Vehicle Connection Management | ST-001 | Covered
|  |  | ST-006 | Covered
|  |  | ST-007 | Covered
REQ-CONN-002 | The GCS shall allow manual network setup (UDP port bindings, TCP hosts, baud rates) for telemetry links. | Vehicle Connection Management | ST-002 | Covered
|  |  | ST-003 | Covered
|  |  | ST-004 | Covered
|  |  | ST-008 | Covered
REQ-CONN-003 | The GCS shall support graceful disconnection of active vehicles and clean release of socket resources. | Vehicle Connection Management | ST-005 | Covered
REQ-GEO-001 | The GCS shall display configured circular or polygon geofences and support altitude boundaries. | Geofence Management | ST-051 | Covered
|  |  | ST-052 | Covered
REQ-GEO-002 | The GCS shall generate warnings and display alert banners immediately (<1.0s) when a vehicle breaches geofence boundaries. | Geofence Management | ST-053 | Covered
|  |  | ST-054 | Covered
|  |  | ST-055 | Covered
REQ-LOG-001 | The GCS main process shall log UI telemetry, IPC payloads, and critical exceptions to local logs. | System Logging | ST-095 | Covered
REQ-LOG-002 | The GCS shall download, store, and review vehicle binary dataflash logs (.bin) and telemetry logs (.tlog) for diagnostics. | System Logging | ST-019 | Covered
REQ-MAP-001 | The GCS shall render a responsive interactive map with coordinate grids, supporting offline tile caching and custom styling. | Map Operations | ST-067 | Covered
REQ-MAP-002 | The GCS map shall trace the vehicle's historic flight path and project its heading in real time. | Map Operations | ST-040 | Covered
REQ-MAV-001 | The GCS shall implement the MAVLink protocol, validating heartbeat message reception at regular intervals. | MAVLink Communication | ST-011 | Covered
|  |  | ST-012 | Covered
|  |  | ST-017 | Covered
|  |  | ST-018 | Covered
|  |  | ST-020 | Covered
REQ-MAV-002 | The GCS shall reject corrupt or malformed MAVLink packets by validating message checksums (CRC). | MAVLink Communication | ST-013 | Covered
REQ-MAV-003 | The GCS shall handle packet sequencing, identifying packet loss and out-of-order delivery issues. | MAVLink Communication | ST-014 | Covered
|  |  | ST-015 | Covered
|  |  | ST-016 | Covered
|  |  | ST-094 | Covered
REQ-MIS-PLAN-001 | The GCS shall support drawing, adding, editing, reordering, and deleting waypoints on the mission planning interface. | Mission Planning | ST-031 | Covered
|  |  | ST-032 | Covered
|  |  | ST-033 | Covered
|  |  | ST-035 | Covered
|  |  | ST-036 | Covered
REQ-MIS-PLAN-002 | The GCS shall allow specifying command actions (e.g., waypoint, takeoff, land, loiter time, ROI) and target altitudes per item. | Mission Planning | ST-034 | Covered
|  |  | ST-037 | Covered
REQ-MIS-TX-001 | The GCS shall execute a multi-step transaction upload handshake to transmit waypoint lists to the UAV, verifying write success. | Mission Upload / Download | ST-038 | Covered
REQ-MIS-TX-002 | The GCS shall download the current mission active in the autopilot, updating the mission editor panel. | Mission Upload / Download | ST-039 | Covered
REQ-MODE-001 | The GCS shall allow the user to switch between supported autopilot flight modes (e.g., Stabilize, AltHold, Loiter, Guided, RTL, Auto). | Flight Mode Management | ST-023 | Covered
|  |  | ST-025 | Covered
|  |  | ST-026 | Covered
REQ-MODE-002 | The GCS shall verify that flight mode transitions complete within 1000ms and are highlighted in the UI header. | Flight Mode Management | ST-024 | Covered
REQ-MVS-001 | The GCS shall auto-discover, track, and isolate telemetry flows for up to 5 vehicles simultaneously on a shared connection port. | Multi-Vehicle Support | ST-081 | Covered
|  |  | ST-083 | Covered
|  |  | ST-084 | Covered
REQ-MVS-002 | The GCS selector tabs shall switch focus, ensuring commands, parameters, and missions are directed only to the active vehicle. | Multi-Vehicle Support | ST-074 | Covered
|  |  | ST-082 | Covered
|  |  | ST-085 | Covered
REQ-PARAM-001 | The GCS shall load full parameter lists from the autopilot and provide search, filter, and categorisation options. | Parameter Management | ST-041 | Covered
|  |  | ST-042 | Covered
|  |  | ST-043 | Covered
|  |  | ST-044 | Covered
REQ-PARAM-002 | The GCS shall write updated parameter values back to the autopilot, validating the write outcome and maintaining local caching. | Parameter Management | ST-045 | Covered
|  |  | ST-046 | Covered
|  |  | ST-047 | Covered
|  |  | ST-048 | Covered
|  |  | ST-049 | Covered
|  |  | ST-050 | Covered
REQ-PERF-001 | The GCS shall maintain a low footprint: CPU utilisation < 15% and RAM heap < 350MB under continuous telemetry stream. | Performance Monitoring | ST-086 | Covered
|  |  | ST-087 | Covered
|  |  | ST-091 | Covered
|  |  | ST-092 | Covered
REQ-PERF-002 | The GCS UI thread shall remain responsive, avoiding frame-drops and keeping event handling latency under 100ms. | Performance Monitoring | ST-088 | Covered
|  |  | ST-089 | Covered
|  |  | ST-090 | Covered
|  |  | ST-093 | Covered
REQ-REC-001 | The GCS shall automatically attempt to reconnect telemetry streams upon link drop within a 2.0s threshold. | Recovery & Reconnection Handling | ST-076 | Covered
|  |  | ST-077 | Covered
|  |  | ST-078 | Covered
|  |  | ST-080 | Covered
REQ-REC-002 | The GCS state manager shall recover parameters and telemetry caches seamlessly across application reloads. | Recovery & Reconnection Handling | ST-079 | Covered
REQ-SET-001 | The GCS shall persist user settings, window sizes, and local directories safely between application restarts. | Settings Management | ST-010 | Covered
REQ-TEL-001 | The GCS shall display live flight parameters including altitude, GPS coordinates, attitude (roll, pitch, yaw), battery voltage, and current flight mode. | Telemetry Monitoring | ST-030 | Covered
|  |  | ST-056 | Covered
|  |  | ST-057 | Covered
|  |  | ST-058 | Covered
|  |  | ST-059 | Covered
|  |  | ST-060 | Covered
|  |  | ST-061 | Covered
|  |  | ST-062 | Covered
|  |  | ST-063 | Covered
|  |  | ST-064 | Covered
REQ-TEL-002 | The GCS HUD and dashboard Gauges shall render telemetry updates smoothly at a telemetry rate of at least 10Hz. | Telemetry Monitoring | ST-065 | Covered
REQ-UI-001 | The GCS shall provide responsive panels (Dashboard, Parameters, Calibration, Camera) loading in under 500ms. | UI Navigation | ST-066 | Covered
|  |  | ST-068 | Covered
REQ-UI-002 | The GCS shall support clean UI scaling, fluid resizing, and a selectable high-contrast theme for outdoor field operations. | UI Navigation | ST-069 | Covered
|  |  | ST-070 | Covered
|  |  | ST-071 | Covered
|  |  | ST-073 | Covered
|  |  | ST-075 | Covered

## Performance_Report
TiHANFly GCS - Performance & Reliability Verification Report
Metric Name | Category | Target Value | Measured Value | Unit | Status
Average CPU Utilization | Performance | 15 | 8.4 | % | PASS
RAM Utilization (Active Session) | Performance | 350 | 245 | MB | PASS
Telemetry Link Latency | Performance | 100 | 45.2 | ms | PASS
Application Startup Time | Performance | 3 | 1.8 | seconds | PASS
Vehicle Connection/Discovery Time | Performance | 5 | 2.1 | seconds | PASS
Mission Upload Time (50 Waypoints) | Performance | 4 | 1.95 | seconds | PASS
Map Render & Offline Tile Load Time | Performance | 2 | 0.85 | seconds | PASS
Continuous Application Uptime | Reliability | 4 | 4 | hours | PASS
Memory Growth Rate (Heap Leak Check) | Reliability | 2 | 0.15 | MB/hour | PASS
Reconnection Success Rate (10 cycles) | Reliability | 100 | 100 | % | PASS
MAVLink Packet Loss Rate | Reliability | 1 | 0.87 | % | PASS
Telemetry Heartbeat Drop Count | Reliability | 0 | 0 | drops | PASS
Application Process Crashes | Reliability | 0 | 0 | crashes | PASS

## Execution_History
TiHANFly GCS - System Testing Regression Run History
Build Number | Execution Date | Total Test Cases | Passed Tests | Failed Tests | Blocked Tests | Pass %
v1.0.0 | 2026-05-15 | 95 | 80 | 15 | 0 | 84.21%
v1.0.1 | 2026-06-01 | 95 | 88 | 7 | 0 | 92.63%
v1.1.0-RC3 | 2026-06-22 | 95 | 91 | 2 | 2 | 95.79%
v1.1.0 | 2026-06-22 | 95 | 95 | 0 | 0 | 100.00%